## How to use
Indie Game Budget Template
Innovecs Games · companion to 'Indie Game Development Cost: A Complete 2026 Budget Breakdown'
How to use it
1. Edit only the yellow cells with blue text. Everything in black is a formula and updates on its own.
2. Start on 'Assumptions': loaded monthly cost per in-house person, contingency, price and net share per copy.
3. On 'Phase budget', set months, in-house headcount, outsourced monthly spend and fixed costs for each phase.
4. Write an exit criterion for every phase. If a phase ends without meeting it, stop and decide before spending the next row.
5. 'Break-even' shows how many copies the total needs to sell. 'Burn check' compares plan and actual month by month.
The example values are the phase-by-phase estimate from the article: a stylized 2D PC game, three salaried founders,
outsourced art, animation and QA. Replace them with your own numbers.
Source for example values: Innovecs Games delivery data, projects scoped 2023 to 2026. Loaded founder cost derived from GDC's 2025 salary report.
These are planning ranges, not a quote.

## Assumptions
Assumptions
Input | Value | Note
Loaded monthly cost per in-house person ($) | 10500 | Salary plus ~30% taxes and benefits. Example: US indie rates, derived from GDC 2025 salary report.
Contingency (share of pre-launch budget) | 15% | 15% to 20% recommended; 20% for a first game.
Launch price ($) | 19.99 | Your planned base price on Steam.
Net share per copy after store cut, sales tax and refunds | 60% | About 60% at full price on Steam (30% store cut, then VAT/sales tax and refunds). Discounts push the real figure lower.

## Phase budget
Phase budget
Yellow cells with blue text are inputs. Cost = months × in-house headcount × loaded cost + months × outsourced monthly spend + fixed costs.
Phase | Months | In-house headcount (avg) | Outsourced spend per month ($) | Fixed costs ($) | What the fixed costs cover | Phase cost ($) | Spent so far ($) | Leave the phase with (exit criterion)
Concept | 1 | 2 | 0 | 0 |  | 21000 | 21000 | A one-page design, a target player, three comparable games and what they sold
Prototype | 2 | 2 | 3000 | 0 | Freelance placeholder art | 48000 | 69000 | A playable loop that outside testers finish and ask to play again
Vertical slice | 2 | 3 | 6500 | 0 |  | 76000 | 145000 | Ten minutes at final quality, a locked art style, a live Steam page
Production | 7 | 3 | 20000 | 30000 | Composer and sound design, fixed fee | 390500 | 535500 | Every level and system in the game, a public demo
Beta and festival | 2 | 3 | 14500 | 30000 | Localization into 5 languages | 122000 | 657500 | A stable release build, wishlists at target, a Next Fest showing
Launch | 1 | 3 | 0 | 40000 | Trailer, key art, PR | 71500 | 729000 | The game on sale
Tools, engine, legal and accounting | 0 | 0 | 0 | 15000 | Across the whole project | 15000 | 744000
Pre-launch subtotal | [5 empty] | 744000
Contingency | [5 empty] | 111600 | 855600
Post-launch support, 6 months | 6 | 1.5 | 0 | 0 |  | 94500 | 950100 | Fixes, a content patch, a console port decision
Total budget | [5 empty] | 950100
Total months to launch | [5 empty] | 15
Note on C14: Example: 2 people for 3 months, then 1 for 3 months = 1.5 average.

## Break-even
Break-even
Total budget ($) | 950100
Net share per copy | 60%
Copies to break even at your launch price | 79214.6073
Price ($) | Net per copy ($) | Copies to break even
9.99 | 5.994 | 158508.5085
14.99 | 8.994 | 105637.0914
19.99 | 11.994 | 79214.6073
24.99 | 14.994 | 63365.3461
29.99 | 17.994 | 52800.9336
Before any publisher share. Most lifetime copies sell on discount, so the real number is higher.

## Burn check
Burn check
Enter planned and actual spend each month, plus milestones planned and closed. Flag rows where money runs ahead of milestones.
Month | Planned spend ($) | Actual spend ($) | Variance ($) | Milestones planned (cumulative) | Milestones closed (cumulative) | Spend vs plan | Milestones vs plan | Warning
1 | 21000 | 21000 | 0 | 1 | 1 | 100% | 100%
2 | 24000 | 26000 | 2000 | 1 | 1 | 104.4% | 100%
3 | 24000 | 25000 | 1000 | 2 | 1 | 104.3% | 50% | Money is ahead of milestones
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
Example rows 1 to 3 show a team 4% over its spending plan while closing half its planned milestones: that is the signal to stop and re-plan.