## How to use
Game port estimate template
Innovecs Games · innovecsgames.com
What this is | A working model for budgeting one game port: labor by work package, the lines a quote leaves out, a second platform, break-even in copies, and a grid for comparing vendor quotes.
Cells to edit | Blue text on yellow fill. Everything else is a formula and recalculates.
Black text | Formulas on the same sheet. Do not overwrite.
Green text | Values pulled from another sheet.
Example values | The numbers already filled in are the worked example from the article: a mid-level 3D game on Unreal Engine 5 going from Steam to PlayStation 5, four people in Eastern Europe for about 16 weeks. They are an illustration, not a quote. Replace them with your own.
Order of use | 1. Pre-quote brief: collect the facts a vendor needs. 2. Estimate: build your own number. 3. Second platform. 4. Break-even: decide whether the port pays, and whether to fund it yourself. 5. Quote comparison: line up the bids you receive.
Sources | Hours, shares and percentages: Innovecs Games delivery data, projects scoped 2023 to 2026. Console store share (30%): documents filed in Epic v. Apple, reported by Kotaku, May 2021. Developer share in console-only publishing deals (63.1% average): Voyer Law review of 100+ agreements, May 2025.

## Estimate
Port estimate, first platform
Blended hourly rate ($) | 55 |  |  | Eastern Europe typically $40 to $70; US and Canada $90 to $150. Source: Innovecs Games delivery data.
Post-launch support, share of labor | 12% |  |  | We advise 10% to 15% for the first three months.
Contingency, share of labor | 15% |  |  | We advise 15% to 20%.
Work package | Hours | Cost ($) | Share of labor | What's in it
Audit and plan | 120 | 6600 | 4.688% | Code and content audit, risk list, milestone plan
Platform bring-up | 240 | 13200 | 9.375% | SDK integration, build pipeline, first boot on a dev kit
Platform features | 320 | 17600 | 12.5% | Accounts, save system, trophies or achievements, suspend and resume, store entitlements
Input and UI adaptation | 400 | 22000 | 15.62% | Controller-first menus, glyphs, text scaling, haptics
Performance and memory | 720 | 39600 | 28.12% | Profiling, streaming, shader and LOD work to a locked frame rate
QA and pre-certification | 440 | 24200 | 17.19% | Functional passes, checklist runs, regression after each optimization
Certification, two cycles | 160 | 8800 | 6.25% | Submission builds and fixes for returned conditions
Production management | 160 | 8800 | 6.25% | Planning, platform holder liaison, reporting
Labor subtotal (the quote) | 2560 | 140800 | 100% | This is the figure most vendor quotes show.
Dev kits, licenses, middleware |  | 8000 |  | Allowance. Xbox dev kit $2,000 (free for approved ID@Xbox projects); Unity Pro $2,310 per seat per year; Sony and Nintendo prices are not public.
Age ratings, store assets, localized store pages |  | 4500 |  | Allowance. Steam $100 per game, Apple $99 a year, Google Play $25 once.
Post-launch support, three months |  | 16896 |  | Labor subtotal x support share.
Contingency |  | 21120 |  | Labor subtotal x contingency share.
Budget to approve |  | 191316
Budget above the quote |  | 35.88% |  | How far the real budget sits above the labor-only number.
Not in this sheet: your own team's time. Plan roughly a day a week from a senior engineer, plus a few hours each from a producer and an art lead.

## Second platform
Adding a second platform
Hours as a share of the first port | 45% | In our projects, a third to half. Higher when the second platform is a step down in hardware.
Fees and hardware for this platform ($) | 5000 | Allowance.
Line | Value | How it is calculated
Hours | 1152 | First-port hours x share
Labor | 63360 | Hours x blended rate
Post-launch support | 7603.2 | Labor x support share
Contingency | 9504 | Labor x contingency share
Fees and hardware | 5000 | From the input above
Second platform budget | 85467.2
First platform budget | 191316 | From the Estimate sheet
Both platforms | 276783.2

## Break-even
How many copies pay for the port
Share of list price the studio keeps | 60% |  |  | After the store's 30% share, sales tax and refunds. Our working assumption; change it to match your territories and discounts.
List price ($) | 19.99 | 29.99 | 39.99 | Edit the three prices.
Net per copy ($) | 11.994 | 17.994 | 23.994
Copies to break even | At price 1 | At price 2 | At price 3 | Budget used
First platform only | 15951 | 10633 | 7974 | 191316
Both platforms | 23077 | 15382 | 11536 | 276783.2
Real break-even points are higher, because many copies sell at a discount.
Pay for the port, or give a publisher a share?
Developer share in a porting-publisher deal | 63.1% |  |  | Average for console-only deals in Voyer Law's review of 100+ publishing agreements (May 2025). Use the figure from your own offer.
Share given up | 36.9%
Net platform revenue where both options cost the same ($) | 518471.5447 |  |  | First-platform budget divided by the share given up.
Copies at that point | At price 1 | At price 2 | At price 3 | Reading
Break-even between paying and sharing | 43228 | 28814 | 21609 | Below this many copies the publisher deal costs less. Above it, paying for the port yourself is cheaper.

## Quote comparison
Comparing vendor quotes
Fill the yellow cells with each bidder's answers. The Example column shows the level of detail to ask for.
Numbers | Example | Vendor A | Vendor B | Vendor C
Quoted price ($) | 140800
Hours in the quote | 2560
Implied hourly rate ($) | 55 | 0 | 0 | 0
Price against your own estimate | 0% | 0% | 0% | 0%
What the quote covers | Example | Vendor A | Vendor B | Vendor C
Which certification passes are included, and how many resubmissions? | Pre-certification plus two submission cycles per platform
Who supplies the dev kits and engine licenses? | Vendor supplies kits; client holds engine licenses
Is post-launch support priced, and for how long? | Three months, 12% of labor, quoted separately
What frame rate and resolution are committed, on which hardware? | 60 fps at 1440p on PS5, measured in three named scenes
Who owns the port branch and build pipeline at handover? | Client, transferred at certification pass
Checks on the partner | Example | Vendor A | Vendor B | Vendor C
Shipped titles on this exact platform, with certification pass dates | Two titles on PS5, passed 2024 and 2025
Dev kits in hand today, and how many | Three PS5 kits on site
Active developer agreements and console engine licenses | Yes for Sony, Microsoft, Nintendo
Who runs certification QA | In-house team of four
Named engineers and the ports they have shipped | Lead engineer named, two prior ports
The last port that failed a submission, and what it cost | One failed cycle in 2024, one week, absorbed by vendor
Two quotes that answer these the same way can be compared on price. Two that do not are quotes for different projects.

## Pre-quote brief
What to send before you ask for a quote
Fact | Your answer | Example
Game and genre |  | 3D action-adventure, single-player
Engine and exact version |  | Unreal Engine 5.4, two engine modifications
Engine modifications |  | Custom streaming for the open hub; patched audio module
Third-party plugins and middleware |  | Wwise, a save plugin, a UI framework; vendor support for PS5 confirmed for two of three
Platforms it ships on today |  | Windows via Steam
Target platforms, in priority order |  | 1. PlayStation 5 2. Nintendo Switch 2
Weakest hardware you must support |  | Switch 2 in handheld mode
Frame rate and resolution targets |  | 60 fps at 1440p on PS5; 30 fps at 1080p docked, 720p handheld on Switch 2
Load time target |  | Under ten seconds from menu to gameplay
Memory and frame time on current min-spec |  | 11GB peak, 14 ms frame time on the Steam minimum spec
Platform features in scope |  | Trophies, cloud saves, suspend and resume; no cross-save
Online features and backend |  | None
Languages |  | Text in eight languages, voice in English
Certification scope |  | Vendor runs pre-certification and submissions on both platforms
Release date or window |  | PS5 in Q2, Switch 2 in Q4
Is the original game still being updated? |  | Two more content patches planned
Licensed IP or licensor approvals |  | None
Who answers questions on your side |  | Tech lead, one day a week; art director for visual sign-off